Holly Hill Primary and Nursery School

Access Plan – September 2025
	Targets


	Strategies.
	Outcome.
	Timeframe.
	Achievements 

	Develop our physical environment with a focus on sensory-friendly approaches. 
	Conduct sensory audits in collaboration with an Occupational Therapist as part of the PINS project. Identify areas needing adjustments such as lighting, noise levels and furniture. Implement changes including sensory zones, noise-cancelling headphones and calming corners.
Complete the PINS project.
	School environment supports sensory needs.
	By September 2026
	PINS action plan created. 

Attended the PINS ‘Supporting Sensory Differences’ conference. 


	Improve classroom language environment

	Work with SALT to conduct language audits in classrooms. Introduce dual coding strategies using visuals and consistent symbols. Provide staff with language development resources and monitor implementation through learning walks.
Complete the PINS project.
	Language-rich, accessible classrooms.
	By September 2026
	PINS action plan created. 

	Ensure all children have access to school trips and residentials
	Review barriers to participation including financial, sensory and emotional needs. Develop inclusive planning checklists and risk assessments. Offer pre-visit familiarisation sessions in school (this may include exploring websites/looking at itineraries) and provide additional adult support where needed.
	All pupils can participate in enriching experiences beyond the classroom

	By September 2026
	All children in the Nest attending the KS1 Sherwood Forest visit.



	(Continue to) Develop whole school approaches to support children with communication and interaction needs across school.  
	Alternatives to daily check in planned for children to express emotions. 

SALT sessions planned weekly. 

SALT strategies in place around school to enable our children to communicate effectively such as on the playground or in the hall. 

Complete the PINS project. 
	Children able to communicate wants and needs more effectively. 
	April 26
	PINS action plan created. 

‘Promoting communication’ training for Foundation and KS1 staff. 

. Language rich environment with dual coding.
 Communication boards around school (including playground) 

Consistent Symbols visible in the classroom


Action Plan to be reviewed – September 2026
